## TimeTable
EVENT PLANNING TIMETABLE |  | Note:
Date of Event: | 2017-06-15 | · Enter your event date in B2 and all deadlines will be accordinly adjusted.
· Not all suggested actions apply to all events.
18-24 Months Before Event | 2015-12-23 | · Timelines may be shortened for simpler events.
• Select potential date options & verify against CNS calendar, University calendar, and religious
holidays calendar to ensure no major conflicts.
• Select final dates.
• Research potetial venues (locations).
• Visit the facilities and do a site inspection.
• Finalize the venue selection.
• Determine if multiple bids are necessary for any service based on $15k - $50K expenditure
(Handbook of Business Practices 7.5.4)
• Negotiate with and get signed contract from facility
• Request a Certificate of Insurance naming the University additonally insured from facility or caterer.
• Reserve sleeping rooms.
• Prepare a preliminary budget.
• Define your audience.
• Develop a program.
• Contact appropriate associations and publications to begin the process of promoting the event.
12-18 Months | 2016-06-15
• Determine theme/title of event.
• Identify planning committees, define committee responsibilities, and select chairpersons.
• Begin search for speakers.
• Plan business and social agenda.
• Establish event budget.
• Determine cost to attendees.
9-12 Months Ahead | 2016-09-18
• Contract with speakers.
• Develop invitation list from various sources. Select and order mailing lists.
• Review program with facility.
6-9 Months | 2016-12-17
• Send first mailing or save-the-date-announcement.
• Design and prepare a printed invitation or conference brochure.
• Design other print materials (registration packets, signs, badges, etc.).
• Maintain contact with speakers and identify audio-visual needs, obtain biographical material for
conference brochure and registration packets.
• Review program with key participants.
• Review and refine budget and committee assignments.
3-5 Months | 2017-03-17
• Establish on-site registration procedure.
• Select on-site personnel.
• Submit OOEF.
• Plan and confirm special event logistics- food and beverage, room set-ups, décor, florals, linens, etc.
• Begin preparation of name badges, registration material, and signage.
• Continue contact with speakers. Confirm their presentation needs and travel/accommodation
arrangements.
• Mail invitations and correspond with participants if appropriate.
• Review and refine budget.
• Develop attendance list from brochure responses; address problem areas where responses are lower
than expected.
• Meet with publicists to begin developing press releases.
2-6 Weeks | 2017-06-01
• Finalize broad agenda.
• Create detailed timelines for each day or component.
• Develop daily staffing schedule and share with on-site personnel.
• Track attendance using an Excel spreadsheet. Note who is attending, who declined, meal choices,
special accomodations, etc. all in one place.
• Select final food and beverage selections. Don’t forget any guests’ dietary accomodations.
• Submit Request to Serve Alcohol.
• Submit Food Distribution Request.
• Confirm all audio-visual arrangements.
• Confirm all room set-up arrangements.
• Review all planning committee activity and make appropriate final assignments to committees
and/or individuals
• Confirm parking and transportation requirements
• Confirm any special ADA accommodations
• Have final program printed
• Have registration packets completed
1 Week Prior | 2017-06-08
• Finalize attendance list and let your vendors know how many people you are expecting.
• Confirm arrangements with all vendors- catering, AV, rentals, speakers, etc. Send them a detailed
event timeline, also known as an event recap, so everyone is on the same page. Include a list
of everyone’s phone numbers for day-of contact.
• Call or e-mail attendees to remind them of the event and to confirm details.
2 Days | 2017-06-13
• Walk through the program at the event site.
• Review program with facility manager.
• Review all details of event recap and assemple pull list (all materials & tools you need on-site)
• Have pre-conference meeting with all appropriate personnel servicing the event.
Day-of-Event | 2017-06-15
• Arrive at least ½ hour before your vendors arrive and at least 2 hours before your guests are slated
to arrive.
• Designate an area for guest inquiries and issues.
• Be sure to stay until the last guest has departed, all vendors are finished breaking down and the
venue has been cleared and cleaned up.
Post-Event
• Send a survey to attendees so you can gather feedback on the event.
• Send thank-you notes to vendors who did an outstanding job.
• Ensure all invoices are paid in a timely manner.
• Create a final budget with all expenses.
• If event will occur again, create notes for future reference r/g what went well and what can be
improved upon.